## 050211 - 050711
WEEKLY STATUS REPORT
Report Date: | 2011-05-07 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Complete SRS Document for "Quản lí Doanh Thu" Module | Nghia Nguyen | In add "Quản lí Hệ thống" Module
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Complete SRS Document for "Quản lí Kho" | Huy Nguyen | Delay 1 day
2 | Complete SRS Document for "Quản lí Cửa hàng" | Nhut Chau | Delay 1 day
3 | Complete Test plan | Tri Nguyen
4 | Complete Test plan | Hai Nguyen
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks
1 | Update SRS Document | Huy Nguyen
2 | Update SRS Document | Nhut Chau
3 | Update SRS Document | Nghia Nguyen
4 | Update SRS Document | Nghiem Doan
5 | Complete Test plan | Tri Nguyen
6 | Complete Test plan | Hai Nguyen

## 050911 - 051411
WEEKLY STATUS REPORT
Report Date: | 2011-05-17 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Update SRS Document | Huy Nguyen | Support for Tri Nguyen to complete Test plan
2 | Update SRS Document | Nhut Chau
3 | Update SRS Document | Nghia Nguyen | Support for Tri Nguyen to complete Test plan
4 | Update SRS Document | Nghiem Doan
5 | Complete Test plan | Tri Nguyen
6 | Complete Test plan | Hai Nguyen | Support for Huy Nguyen to complete SRS Document
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Estimate for plan in this week | Huy Nguyen | Not accurate. Defect when estimate human resources
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
1 | Have problems when analysis Business Process | Team | Members to think for themselves Many defects made delay plan
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks
1 | Design structure for TeamAssignment # 4 | Tri Nguyen
Nhut Chau
2 | Review and update SRS and Test plan Document | Team

## 051611 - 052111
WEEKLY STATUS REPORT
Report Date: | 2011-05-22 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Design structure for TeamAssignment # 4 | Tri Nguyen
Nhut Chau
2 | Review and update SRS Document | Nghia Nguyen | - Nghia Nguyen design user interface - Training for Hai Nguyen and Nghiem Doan about SRS Document
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Update SRS Document | Team | Just complete Usecase Description, imcomplete interface
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks
1 | Complete team assignment 4 CS | Team
2 | Design Database [draft ver] | Team

## 052311 - 052811
WEEKLY STATUS REPORT
Report Date: | 2011-05-25 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Complete Usecase Description for "Danh mục sách" | Nghiem Doan
2 | Develop Sale function for Team Assignment 04 | Hai Nguyen
3 | Design structure for Team Assignment 04 | Tri Nguyen
4
5
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks