## 050211 - 050711 (hidden)
WEEKLY STATUS REPORT
Report Date: | 2011-05-07 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Complete SRS Document for "Quản lí Doanh Thu" Module | Nghia Nguyen | In add "Quản lí Hệ thống" Module
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Complete SRS Document for "Quản lí Kho" | Huy Nguyen | Delay 1 day
2 | Complete SRS Document for "Quản lí Cửa hàng" | Nhut Chau | Delay 1 day
3 | Complete Test plan | Tri Nguyen
4 | Complete Test plan | Hai Nguyen
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks
1 | Update SRS Document | Huy Nguyen
2 | Update SRS Document | Nhut Chau
3 | Update SRS Document | Nghia Nguyen
4 | Update SRS Document | Nghiem Doan
5 | Complete Test plan | Tri Nguyen
6 | Complete Test plan | Hai Nguyen

## 050911 - 051411 (hidden)
WEEKLY STATUS REPORT
Report Date: | 2011-05-17 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Update SRS Document | Huy Nguyen | Support for Tri Nguyen to complete Test plan
2 | Update SRS Document | Nhut Chau
3 | Update SRS Document | Nghia Nguyen | Support for Tri Nguyen to complete Test plan
4 | Update SRS Document | Nghiem Doan
5 | Complete Test plan | Tri Nguyen
6 | Complete Test plan | Hai Nguyen | Support for Huy Nguyen to complete SRS Document
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Estimate for plan in this week | Huy Nguyen | Not accurate. Defect when estimate human resources
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
1 | Have problems when analysis Business Process | Team | Members to think for themselves Many defects made delay plan
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks
1 | Design structure for TeamAssignment # 4 | Tri Nguyen
Nhut Chau
2 | Review and update SRS and Test plan Document | Team

## 051611 - 052111 (hidden)
WEEKLY STATUS REPORT
Report Date: | 2011-05-22 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Design structure for TeamAssignment # 4 | Tri Nguyen
Nhut Chau
2 | Review and update SRS Document | Nghia Nguyen | - Nghia Nguyen design user interface - Training for Hai Nguyen and Nghiem Doan about SRS Document
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Update SRS Document | Team | Just complete Usecase Description, imcomplete interface
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks
1 | Complete team assignment 4 CS | Team
2 | Design Database [draft ver] | Team

## 052311 - 052811 (hidden)
WEEKLY STATUS REPORT
Report Date: | 2011-05-29 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Complete Usecase Description for "Danh mục sách" | Nghiem Doan
2 | Develop Team Assignment 04 | Nghia Nguyen
3 | Develop Team Assignment 04 | Tri Nguyen
4 | Description of the problem for database (Section 2) | Hai Nguyen
5 | Modeling ERD Model | Nhut Chau
6 | Update SRS Document | Team
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Design ERD | Team
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks
1 | Start MiniProject CS
2 | Start TeamAssignment Testing

## 053011 - 060411 (hidden)
WEEKLY STATUS REPORT
Report Date: | 2011-06-05 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Translate "Frontier" section for MiniProject CS | Huy Nguyen
2 | Translate "History and Page Repository" section for MiniProject CS | Hai Nguyen
3 | Translate "Fetching" section for MiniProject CS | Nghia Nguyen
4 | Translate "Parsing" section for MiniProject CS | Nhut Chau
5 | Translate "HTML tag tree" section for MiniProject CS | Nghiem Doan
6 | Translate "Multi-threaded crawler" section for MiniProject CS | Tri Nguyen
7 | Translate "Summary" and "Introduction" section | Tri Nguyen
Nghia Nguyen
8 | Publish requirement on TFS | Team
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks
1 | Update Test plan Document | Team
2 | Update SRS Document | Team
3 | Update Database Document | Team
4 | Modeling flowchart for Miniproject CS | Team

## 061311 - 061811 (hidden)
WEEKLY STATUS REPORT
Report Date: | 2011-06-18 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Draw sequence diagram for MyCrawler2.java | Nhut Chau
2 | Comment for MyCrawler2.java | Nhut Chau
3 | Draw sequence diagram for MyCrawler1.java | Tri Nguyen | Delay one week. Because last week team relax
4 | Update "Danh mục" Module | Nghiem Doan
5 | Update "Quản lí hệ thống" Module | Hai Nguyen
6 | Update "Quản lí bán hàng" Module | Nghia Nguyen
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
1 | Problems arise from update Module |  | "Quản lí hệ thống" and "Quản lí bán hàng" Module
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks
1 | Complete Document and Start develop for MiniProject
2 | Complete assigned task for FinalProjet of CS

## 062011 - 062511 (hidden)
WEEKLY STATUS REPORT
Report Date: | 2011-06-25 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Integrate interface | Team
2 | Design interface for WebCrawler | Nghia Nguyen | Supporter: Tri Nguyen and Nhut Chau
3 | Modify database design | Nhut Chau
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
1 | Problems about design database
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks
1 | Modify Design database | Team
2 | Update Usecase description | Team
3 | Update Testcase | Team
4 | Develop source code for MiniProject and FinalProject | Team

## 062711 - 070211 (hidden)
WEEKLY STATUS REPORT
Report Date: | 2011-07-02 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Integrate interface | Team
2 | Modify Document | Team
3 | Develop Source code for MiniProject | Team
4 | Modify Source code for WebCrawler | Tri Nguyen | Supporter: Nghia Nguyen
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Complete Test plan | Huy Nguyen
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks
1 | Develop source code for MiniProject and FinalProject | Team
2 | Update Testplan | Huy Nguyen

## 070411 - 070911
WEEKLY STATUS REPORT
Report Date: | 2011-07-09 | Team: | 1
PLANED & ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Complete Source code for FinalProject CS | Tri Nguyen | Hai Nguyen support comment
2 | Complete Document for FinalProject CS | Team
3 | Test fucntion for application WebCrawler | Nghia Nguyen | Nghiem Doan
4 | Integrate document for MiniProject | Nghia Nguyen | Nghiem Doan support
5 | Develop source code | Huy Nguyen
Hai Nguyen
Nhut Chau
PLANED BUT NOT ACCOMPLISHED
No. | Tasks | Responsibility | Remarks
1 | Complete Sequence Diagram | Nhut Chau
2 | Complete Algorithm Document | Tri Nguyen
UNPLANED ACTIVITY UNDERTAKEN
No. | Tasks | Responsibility | Remarks
PLAN FOR NEXT WEEK
No. | Tasks | Responsibility | Remarks
1 | Develop source code
2 | Complete Document